## Sheet1
MIST7590E/7591E Smithgall Woods WBS/Project Plan | [10 empty] | 2017 | [15 empty] | 2018
Task or Deliverable - WBS |  |  |  | Duration (hr) | Planned Start Date | Actual Start Date | Planned Completion Date | Actual Completion Date | Completion Percentage | Owner(s) | 2017-08-16 | 2017-08-23 | 2017-08-30 | 2017-09-06 | 2017-09-13 | 2017-09-20 | 2017-09-27 | 2017-10-04 | 2017-10-11 | 2017-10-18 | 2017-10-25 | 2017-11-01 | 2017-11-08 | 2017-11-15 | 2017-11-30 | 2017-12-08 | 2017-01-04 | 2017-01-11 | 2017-01-18 | 2017-01-25 | 2017-02-01 | 2017-02-08 | 2017-02-15 | 2017-02-22 | 2017-03-01 | 2017-03-08 | 2017-03-15 | 2017-03-22 | 2017-03-29 | 2017-04-05 | 2017-04-12 | 2017-04-19 | 2017-04-26
1.0 Initiate Project |  |  |  |  | 2017-08-23 | 2017-08-23 | 2017-11-30
| 1.1 Identify Stakeholders |  |  | 1 | 2017-08-28 | 2017-08-28 | 2017-09-01 | 2017-11-22 | 100% | Eliseo
| 1.2 Develop Project Charter |  |  |  | 2017-09-01 | 2017-09-01 | 2017-11-30 |  | Late
|  | 1.2.1 Define Scope |  | 1 | 2017-09-01 | 2017-09-01 | 2017-09-14 | 2017-09-14 | 100% | ALL
|  | 1.2.2 Define Security Remediation Plan (Site Maintenance) |  | 7 | 2017-09-01 | 2017-09-01 | 2017-09-06 | 2017-09-06 | 100% | Jennifer
|  | 1.2.3 Define Requirements |  | 18 | 2017-09-14 | 2017-09-14 | 2017-09-24 | 2017-09-24 | 100% | Andrea
|  | 1.2.4 Define Roles |  | 1 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 100% | Eliseo
|  | 1.2.5 Identify Controls |  | 3 | 2017-09-25 | 2017-09-26 | 2017-09-28 | 2017-09-28 | 100% | ALL
|  | 1.2.6 Identify Risks |  | 2 | 2017-09-28 | 2017-09-28 | 2017-09-30 | 2017-09-30 | 100% | ALL
|  | 1.2.7 Finalize Charter |  |  | 2017-11-03 | 2017-11-03 | 2017-11-30 |  | 100% | ALL
|  |  | 1.2.7.1 Conduct Stakeholder Review | 2 | 2017-11-03 | 2017-11-03 | 2017-11-27 | 2017-11-26 | 100% | ALL
|  |  | 1.2.7.2 Obtain Stakeholder Approval | 2 | 2017-11-27 | 2017-11-27 | 2017-11-30 |  | Late | Eliseo
2.0 Plan Project |  |  |  |  | 2017-09-26 | 2017-09-26 | 2017-11-12 | 2017-11-12 | 100%
| 2.1 Develop Project Plan |  |  |  | 2017-09-26 | 2017-09-26 | 2017-10-10 | 2017-10-10 | 100%
|  | 2.1.1 Develop Work Breakdown Structure |  | 3 | 2017-09-26 | 2017-09-26 | 2017-10-10 | 2017-10-10 | 100% | ALL
|  | 2.1.2 Develop Project Timeline |  | 1 | 2017-09-26 | 2017-09-26 | 2017-10-10 | 2017-10-10 | 100% | ALL
|  | 2.1.3 Assign Project Responsibilities |  | 1 | 2017-09-26 | 2017-09-26 | 2017-10-10 | 2017-10-10 | 100% | Eliseo
| 2.2 Develop Project Control Plan |  |  |  | 2017-09-26 | 2017-09-26 | 2017-10-10 | 2017-10-10 | 100%
|  | 2.2.1 Develop Communication Plan |  |  | 2017-09-26 | 2017-09-26 | 2017-10-10 | 2017-10-10 | 100% | Andrea
|  |  | 2.2.1.1 Finalize Team Collaboration Tool Selection | 1 | 2017-09-26 | 2017-09-26 | 2017-10-10 | 2017-10-10 | 100% | ALL
|  |  | 2.2.1.2 Finalize Version Control Tool Selection | 1 | 2017-09-26 | 2017-09-26 | 2017-10-10 | 2017-10-10 | 100% | ALL
|  | 2.2.2 Develop Quality Management Plan |  | 2 | 2017-09-26 | 2017-09-26 | 2017-10-10 | 2017-10-10 | 100% | Clark
|  | 2.2.3 Develop Change Control Management Plan |  | 2 | 2017-09-26 | 2017-09-26 | 2017-10-10 | 2017-10-10 | 100% | Alex
|  | 2.2.4 Develop Assumptions and Risks |  | 2 | 2017-09-26 | 2017-09-26 | 2017-10-10 | 2017-10-10 | 100% | Jennifer
|  | 2.2.5 Develop Human Resources Plan |  | 2 | 2017-09-26 | 2017-09-26 | 2017-10-10 | 2017-10-10 | 100% | Andrea
|  | 2.2.6 Develop Code Test Management Plan |  | 2 | 2017-09-26 | 2017-09-26 | 2017-10-10 | 2017-10-10 | 100% | Eliseo
| 2.3 Develop Logical Models |  |  |  | 2017-09-26 | 2017-09-26 | 2017-10-10 | 2017-10-10 | 100%
|  | 2.3.1 Develop Use Cases |  | 2 | 2017-09-26 | 2017-09-26 | 2017-10-10 | 2017-10-10 | 100% | Jennifer, Andrea
|  | 2.3.2 Develop User Stories |  | 2 | 2017-09-26 | 2017-09-26 | 2017-10-10 | 2017-10-10 | 100% | Alex, Clark
|  | 2.3.3 Develop Workflows |  | 4 | 2017-09-26 | 2017-09-26 | 2017-10-10 | 2017-10-10 | 100% | Alex, Clark
|  | 2.3.4 Develop Data Models |  | 2 | 2017-09-26 | 2017-09-26 | 2017-10-10 | 2017-10-10 | 100% | Eliseo
|  | 2.3.5 Develop Wireframes |  | 3 | 2017-09-26 | 2017-09-26 | 2017-10-10 | 2017-10-10 | 100% | Alex
|  | 2.3.6 Develop Site Map |  | 3 | 2017-11-08 | 2017-11-08 | 2017-11-12 | 2017-11-12 | 100% | ALL
| 2.4 Research Web CMS tool and Site Host |  |  | 4 | 2017-11-08 | 2017-11-08 | 2017-11-12 | 2017-11-12 | 100% | ALL
3.0 Conduct Usability Test |  |  |  |  | 2017-10-20 | 2017-10-20 | 2017-10-26 | 2017-10-26 | 100%
| 3.1 Develop HTML/JS website prototype for demo |  |  |  | 2017-10-20 | 2017-10-20 | 2017-10-25 | 2017-10-25 | 100% | Alex
|  | 3.1.1 Build basic website for text/photo update |  | 4 | 2017-10-20 | 2017-10-20 | 2017-10-25 | 2017-10-25 | 100% | Alex
|  | 3.1.2 Develop user guide for demo |  | 3 | 2017-10-20 | 2017-10-20 | 2017-10-25 | 2017-10-25 | 100% | Alex
| 3.2 Develop test cases for Wordpress site update |  |  | 2 | 2017-10-20 | 2017-10-20 | 2017-10-23 | 2017-10-23 | 100% | Jennifer
| 3.3 Schedule test with stakeholder |  |  | 1 | 2017-10-20 | 2017-10-20 | 2017-10-24 | 2017-10-24 | 100% | Eliseo
| 3.4 Conduct test and record video of test |  |  | 1 | 2017-10-24 | 2017-10-24 | 2017-10-26 | 2017-10-26 | 100% | ALL
4.0 Build and Test the Site & Volunteer Application |  |  |  |  | 2017-12-11 |  | 2018-03-15
| 4.1 Create the Database |  |  |  | 2017-12-11 |  | 2017-12-15 |  |  | Clark
|  | 4.1.1 Load constant/attribute values |  |  | 2017-12-11 |  | 2017-12-15
| 4.2 Write the Code - Increment 1 |  |  |  | 2017-12-11 |  | 2018-01-25 |  |  | ALL
| 4.3 Test the Site and App - Increment 1 |  |  |  | 2018-01-26 |  | 2018-01-31 |  |  | Eliseo, Clark
|  | 4.3.1 Test Application Flow |  |  | 2018-01-26 |  | 2018-01-31 |  |  | ALL
|  | 4.3.2 Test Application Content |  |  | 2018-01-26 |  | 2018-01-31 |  |  | ALL
|  | 4.3.3 Test Application Logic |  |  | 2018-01-26 |  | 2018-01-31 |  |  | ALL
|  | 4.3.4 Adjust Application |  |  | 2018-01-26 |  | 2018-01-31 |  |  | ALL
| 4.4 Write the Code - Increment 2 |  |  |  | 2018-01-26 |  | 2018-02-23 |  |  | ALL
| 4.5 Test the Site and App - Increment 2 |  |  |  | 2018-02-24 |  | 2018-03-02 |  |  | ALL
| 4.6 Conduct Stakeholder Review |  |  |  | 2018-03-14 |  | 2018-03-15 |  |  | ALL
5.0 Deploy Website and Volunteer Application |  |  |  |  | 2018-03-31 |  | 2018-04-04 |  |  | Eliseo, Jennifer
| 5.1 Prep Code for Move to Production |  |  |  | 2018-03-31 |  | 2018-04-02 |  |  | ALL
| 5.2 Move to Production |  |  |  | 2018-03-31 |  | 2018-04-04 |  |  | Eliseo, Jennifer
| 5.3 Transfer Ownership to Client |  |  |  | 2018-03-31 |  | 2018-04-04 |  |  | Eliseo, Jennifer
|  | 5.3.1 Train Client |  |  | 2018-03-31 |  | 2018-04-04 |  |  | ALL
|  | 5.3.2 Transfer electronic content to client |  |  | 2018-03-31 |  | 2018-04-04 |  |  | ALL
6.0 Develop Project Communication Material |  |  |  |  | 2017-12-04 |  | 2018-04-27 |  |  | ALL
| 6.1 Develop User Manual/Documentation |  |  |  | 2018-03-02 |  | 2018-03-30 |  |  | Andrea, Clark
| 6.2 Develop Project Deliverables |  |  |  | 2017-12-04 |  | 2018-04-27 |  |  | Eliseo
|  | 6.2.1 Develop Term I Project Binder |  |  | 2017-12-04 |  | 2017-12-08 |  |  | ALL
|  | 6.2.2 Develop Term II Project Binder |  |  | 2018-04-16 |  | 2018-04-27 |  |  | ALL
|  | 6.2.3 Develop Final Project Presentation |  |  | 2018-04-16 |  | 2018-04-27 |  |  | ALL
7.0 Update PHP, WordPress Themes & Plugins (Site Maintenance) |  |  |  | 2 | 2017-10-30 | 2017-10-30 | 2017-10-31 | 2017-10-31 | 100% | Jennifer
8.0 Restore Volunteer Reports site (Site Maintenance) |  |  |  | 5 | 2017-11-09 | 2017-11-09 | 2017-11-12 | 2017-11-12 | 100% | Jennifer