## Sheet1
Instruction: For each of the following tasks, please provide your inputs on the Smithgall Woods Project Charter document in GitHub by the due date.
Task | Assigned to | Due Date | Tools
Use Case Diagram - Volunteer Sign-up/Log | Jennifer | 2017-10-01 | https://go.gliffy.com/go/html5/launch#
Use Case Diagram - Admin | Andrea | 2017-10-01
User Stories - Volunteer | Alex | 2017-10-01
2017-10-01
User Stories - Admin | Clark | 2017-10-01
Data Model - Volunteer | Eliseo | 2017-10-01
Data Model - Admin | Eliseo | 2017-10-01
Workflow Diagram - Volunteer | Clark | 2017-10-08 | https://go.gliffy.com/go/html5/launch#
Workflow Diagram - Friends of SW |  | 2017-10-08
Workflow Diagram - Cabin Reservation |  | 2017-10-08
Workflow Diagram - Admin | Alex | 2017-10-08
Instruction: Please describe each of the following topic/plan based on the scope of this project with sufficient details. Refer to the 2015 MLC Project Charter for example.
Assumptions and Risks | Jennifer | 2017-10-08
Communication Plan | Andrea | 2017-10-08
Scope Management Plan | Eliseo | 2017-10-08
Quality Management Plan | Clark | 2017-10-08
Change Control Management Plan | Alex | 2017-10-08
Human Resources Plan | Andrea | 2017-10-08
Test Plan | Eliseo | 2017-10-08
Implementation and Closure Plan | Jennifer | 2017-10-08