## Planning Tasks
Instruction: For each of the following tasks, please provide your inputs on the Smithgall Woods Project Charter document in GitHub by the due date.
Task | Assigned to | Due Date | Tools
Use Case Diagram - Volunteer Sign-up/Log | Jennifer | 2017-10-01 | https://go.gliffy.com/go/html5/launch#
Use Case Diagram - Admin | Andrea | 2017-10-01 | http://alexdp.free.fr/violetumleditor/page.php
User Stories - Volunteer | Alex | 2017-10-01
2017-10-01
User Stories - Admin | Clark | 2017-10-01
Data Model - Volunteer | Eliseo | 2017-10-01
Data Model - Admin | Eliseo | 2017-10-01
Workflow Diagram - Volunteer | Clark | 2017-10-08 | https://go.gliffy.com/go/html5/launch#
Workflow Diagram - Friends of SW |  | 2017-10-08
Workflow Diagram - Cabin Reservation |  | 2017-10-08
Workflow Diagram - Admin | Alex | 2017-10-08 | https://demo.bpmn.io/
Instruction: Please describe each of the following topic/plan based on the scope of this project with sufficient details. Refer to the 2015 MLC Project Charter for example.
Assumptions and Risks | Jennifer | 2017-10-08
Communication Plan | Andrea | 2017-10-08
Scope Management Plan | Eliseo | 2017-10-08
Quality Management Plan | Clark | 2017-10-08
Change Control Management Plan | Alex | 2017-10-08
Human Resources Plan | Andrea | 2017-10-08
Test Plan | Eliseo | 2017-10-08
Implementation and Closure Plan | Jennifer | 2017-10-08

## Rebuild Tasks
Instruction: Before you begin working on your assigned task, please watch the tutorials on WordPress & PHP.
Site & App Rebuild Task | Assigned to | First Iteration Due Date | Final Iteration Due Date | Notes
Home Page & Search Feature |  | 2018-01-19 | 2018-02-16 | Choose a theme for all site pages
About Us Friends & Activities |  | 2018-01-19 | 2018-02-16 | Choose a theme for all site pages
Events & Volunteer Opportunities |  | 2018-01-19 | 2018-02-16 | Choose a theme for all site pages
Friends Corner, Visitors & Contact Us |  | 2018-01-19 | 2018-02-16 | Choose a theme for all site pages
Volunteer Hours App: |  |  |  | Choose a theme for all site pages
-- Create User Account / Login |  | 2018-01-19 | 2018-02-16
-- Add & View Volunteer Hours |  | 2018-01-19 | 2018-02-16
-- Edit Profile / Password / Interest |  | 2018-01-19 | 2018-02-16
-- View FAQs |  | 2018-01-19 | 2018-02-16
Volunteer Hours Database |  | 2017-12-20 |  | DB must be created before building the app use cases
Volunteer Reports App:
-- Select by Name |  | 2018-01-19 | 2018-02-16
-- Select by Activity |  | 2018-01-19 | 2018-02-16
-- Select by Location |  | 2018-01-19 | 2018-02-16
-- Select by Project |  | 2018-01-19 | 2018-02-16